## Tasks
Task Name | Phase | Start Date | Due Date | Status | Priority | Assigned To | Email | % Complete | Description | Notes | Milestone
Project Kickoff Meeting | Planning | 2025-01-06 | 2025-01-06 | Completed | High | Sarah Chen | s.chen@contoso.com | 100 | Align all stakeholders on project goals, budget, and delivery timeline. | All department leads attended; budget of $180k approved. | Yes
Define Conference Theme & Goals | Planning | 2025-01-07 | 2025-01-17 | Completed | High | Sarah Chen | s.chen@contoso.com | 100 | Establish conference vision, key messages, and success metrics. | Theme selected: "Innovate Together". Target: 500+ attendees.
Venue Research & Shortlist | Planning | 2025-01-13 | 2025-01-24 | Completed | Critical | Marcus Webb | m.webb@contoso.com | 100 | Research venues with capacity 500+, AV capability, and in-house catering. | 3 venues shortlisted; Grand Convention Center ranked #1.
Venue Selection & Contract Signed | Planning | 2025-01-27 | 2025-02-07 | Completed | Critical | Marcus Webb | m.webb@contoso.com | 100 | Finalize venue selection and execute contract. | Grand Convention Center booked for Jun 2–3. Deposit paid. | Yes
Budget Approved by Finance | Planning | 2025-02-03 | 2025-02-14 | Completed | Critical | Sarah Chen | s.chen@contoso.com | 100 | Secure full $180,000 project budget approval from CFO. | Approved with 5% contingency reserve. Tracked in Finance portal. | Yes
Keynote Speaker Outreach | Content | 2025-02-10 | 2025-03-07 | Completed | High | Priya Nair | p.nair@contoso.com | 100 | Contact and confirm 3 keynote speakers for main stage. | All 3 keynotes confirmed. Bios received and approved.
Breakout Session Speaker Recruitment | Content | 2025-02-24 | 2025-03-28 | Completed | High | Priya Nair | p.nair@contoso.com | 100 | Recruit 12 speakers for 6 breakout sessions (2 per session). | 10 confirmed, 2 alternates confirmed as backup.
Full Agenda Finalized & Published | Content | 2025-03-31 | 2025-04-11 | Completed | High | Priya Nair | p.nair@contoso.com | 100 | Publish complete agenda with speaker bios and session descriptions. | Agenda live on website. PDF version distributed to sponsors. | Yes
Post-Event Survey Design | Content | 2025-04-28 | 2025-05-09 | In Progress | Medium | Priya Nair | p.nair@contoso.com | 60 | Design attendee satisfaction survey targeting NPS > 60. | Draft in SurveyMonkey. Review with Sarah by May 7.
AV & Production Vendor Selection | Logistics | 2025-02-17 | 2025-03-14 | Completed | High | Marcus Webb | m.webb@contoso.com | 100 | Select AV production company for main stage, 3 breakout rooms, and streaming. | ProSound AV contracted. Includes live-stream package.
Catering Menu & Contract | Logistics | 2025-02-24 | 2025-03-21 | Completed | Medium | Marcus Webb | m.webb@contoso.com | 100 | Finalize catering for 500 attendees across 2 full days. | Menu confirmed. Halal, vegan, and gluten-free options included.
Speaker Travel & Hotel Coordination | Logistics | 2025-04-07 | 2025-05-02 | In Progress | Medium | Marcus Webb | m.webb@contoso.com | 60 | Book flights and hotel accommodation for all out-of-town speakers. | 8 of 10 speakers fully booked. 2 awaiting flight confirmation.
Badge & Swag Production | Logistics | 2025-04-14 | 2025-05-09 | In Progress | Low | Marcus Webb | m.webb@contoso.com | 40 | Design and print name badges; procure branded tote bags and lanyards. | Badge design approved. Print order placed — delivery May 5.
Volunteer Recruitment & Training | Logistics | 2025-04-21 | 2025-05-16 | In Progress | Medium | Jess Okafor | j.okafor@contoso.com | 50 | Recruit 30 event-day volunteers and run a 2-hour orientation session. | 22 volunteers confirmed. Orientation scheduled for May 14.
Rehearsal & AV Tech Run-Through | Logistics | 2025-05-29 | 2025-05-30 | Not Started | Critical | Marcus Webb | m.webb@contoso.com | 0 | Full stage rehearsal with AV team and all keynote speakers. | All speakers must attend. Backup AV team on standby. | Yes
Conference Day 1 Execution | Logistics | 2025-06-02 | 2025-06-02 | Not Started | Critical | Sarah Chen | s.chen@contoso.com | 0 | Execute Day 1: registration open, 2 keynotes, 6 breakouts, evening reception. | Doors open 7:30 AM. Live-stream goes live at 9 AM. | Yes
Conference Day 2 Execution | Logistics | 2025-06-03 | 2025-06-03 | Not Started | Critical | Sarah Chen | s.chen@contoso.com | 0 | Execute Day 2: workshops, panel discussions, closing keynote, awards ceremony. | Post-event survey email to go live at 4 PM. | Yes
Post-Event Venue Debrief | Logistics | 2025-06-09 | 2025-06-13 | Not Started |  | Marcus Webb | m.webb@contoso.com | 0 | Review venue performance with event manager; document lessons learned. | Required for 2026 venue renewal negotiation.
Registration Platform Setup | Marketing | 2025-03-10 | 2025-03-28 | Completed | High | Jess Okafor | j.okafor@contoso.com | 100 | Configure Eventbrite with early-bird and standard pricing tiers. | 312 early-bird registrations in first week.
Conference Website Launch | Marketing | 2025-03-17 | 2025-04-04 | Completed | High | Jess Okafor | j.okafor@contoso.com | 100 | Launch public conference website with agenda, speakers, and sponsor info. | Live at techconf2025.contoso.com. 4,200 unique visitors in week 1. | Yes
Social Media Campaign — Phase 1 | Marketing | 2025-03-24 | 2025-04-18 | Completed | Medium | Jess Okafor | j.okafor@contoso.com | 100 | LinkedIn and Twitter campaign to drive early-bird ticket sales. | Engagement rate 4.2% above baseline. 180 tickets sold via social.
Sponsorship Packages Closed | Marketing | 2025-03-03 | 2025-04-25 | In Progress | High | Sarah Chen | s.chen@contoso.com | 80 | Close Gold, Silver, and Bronze sponsorship packages. | 4 of 6 slots filled. 2 negotiations active — close expected by Apr 18.
Social Media Campaign — Phase 2 | Marketing | 2025-05-05 | 2025-06-01 | Not Started | Medium | Jess Okafor | j.okafor@contoso.com | 0 | Final countdown posts, speaker spotlights, and live-day social coverage. | Coordinate speaker takeover content. Schedule posts via Buffer.
Final Attendee Confirmation Emails | Marketing | 2025-05-19 | 2025-05-23 | Not Started |  | Jess Okafor | j.okafor@contoso.com | 0 | Send final logistics email to registered attendees with schedule and parking. | Registration closes May 16. Use Mailchimp template #Conference-Final.
Sponsor Debrief & 2026 Renewals | Marketing | 2025-06-04 | 2025-06-20 | Not Started | High | Sarah Chen | s.chen@contoso.com | 0 | Present ROI metrics to all sponsors; pitch 2026 renewal packages. | Pre-meeting decks due June 9. Target 80% renewal rate.