## Tasks
Task Name | Phase | Start Date | Due Date | Status | Priority | Assigned To | Email | % Complete | Description | Notes | Milestone
Discovery Kickoff | Discovery & Strategy | 2026-06-02 | 2026-06-02 | Completed | High | Sarah Chen | s.chen@contoso.com | 100 | Align stakeholders on project scope, goals, timeline, and success metrics. | All department leads attended. Scope document signed off. | Yes
Current Site Audit | Discovery & Strategy | 2026-06-03 | 2026-06-10 | Completed | High | Marcus Webb | m.webb@contoso.com | 100 | Audit existing site: content inventory, analytics, SEO performance, and technical debt. | 47 pages inventoried. Core Web Vitals failing on 12 pages. Full report in Drive.
Competitive Analysis | Discovery & Strategy | 2026-06-05 | 2026-06-13 | Completed | Medium | Priya Nair | p.nair@contoso.com | 100 | Analyse 5 competitor sites for UX, content strategy, and feature parity. | Key findings: competitors are strong on mobile; we lag on load time and accessibility.
Stakeholder Interviews | Discovery & Strategy | 2026-06-08 | 2026-06-18 | Completed | High | Sarah Chen | s.chen@contoso.com | 100 | Conduct 1:1 interviews with 8 internal stakeholders and 3 key customers. | 11 interviews completed. Themes: navigation confusion, slow search, missing pricing info.
Strategy & Goals Document Approved | Discovery & Strategy | 2026-06-19 | 2026-06-23 | Completed | Critical | Sarah Chen | s.chen@contoso.com | 100 | Finalise and get sign-off on the website strategy, KPIs, and information architecture. | Approved by CMO and CEO on June 23. | Yes
Information Architecture | Design | 2026-06-22 | 2026-07-01 | Completed | High | Jess Okafor | j.okafor@contoso.com | 100 | Define new site map, navigation structure, and content hierarchy. | Reduced top-level nav from 9 items to 5. Card sort validated with 20 users.
Wireframes — Core Pages | Design | 2026-07-01 | 2026-07-16 | Completed | High | Jess Okafor | j.okafor@contoso.com | 100 | Low-fidelity wireframes for Home, Product, About, Contact, and Blog templates. | All 5 templates approved after second review. Figma: figma.com/file/wireframes
Brand & Visual Design System | Design | 2026-07-10 | 2026-07-28 | In Progress | High | Jess Okafor | j.okafor@contoso.com | 75 | Develop updated color palette, typography, component library, and brand guidelines. | Colors and type approved. Component library 75% complete. Icons pending.
High-Fidelity Mockups | Design | 2026-07-24 | 2026-08-08 | In Progress | High | Jess Okafor | j.okafor@contoso.com | 30 | Full high-fidelity designs for all core page templates — desktop and mobile. | Home and Product pages complete. About and Contact in progress.
Accessibility Review (Design) | Design | 2026-08-06 | 2026-08-13 | Not Started | High | Marcus Webb | m.webb@contoso.com | 0 | Review all designs for WCAG 2.1 AA compliance: contrast ratios, focus states, touch targets. | Use axe DevTools and manual review checklist.
Design Sign-Off | Design | 2026-08-14 | 2026-08-14 | Not Started | Critical | Sarah Chen | s.chen@contoso.com | 0 | Final stakeholder approval of all high-fidelity designs before development begins. | Required before any development work commences. | Yes
Dev Environment & CMS Setup | Development | 2026-08-17 | 2026-08-21 | Not Started | Critical | Marcus Webb | m.webb@contoso.com | 0 | Set up staging server, CMS (Contentful), CI/CD pipeline, and repository structure. | Target stack: Next.js 14, Contentful, Vercel.
Global Layout & Navigation | Development | 2026-08-21 | 2026-09-03 | Not Started | High | Marcus Webb | m.webb@contoso.com | 0 | Build header, footer, navigation, and responsive grid system from design system. | Must pass Lighthouse performance score ≥ 90.
Core Page Templates | Development | 2026-09-01 | 2026-09-19 | Not Started | High | Marcus Webb | m.webb@contoso.com | 0 | Build Home, Product, About, Contact, and Blog list/detail page templates. | All templates must be fully responsive (320px–2560px) and CMS-driven.
Search & Filtering | Development | 2026-09-15 | 2026-09-26 | Not Started | High | Dave Chen | d.chen@contoso.com | 0 | Implement site-wide search with filtering, sorting, and instant results. | Using Algolia. Index must include products, blog posts, and documentation.
Forms & Integrations | Development | 2026-09-22 | 2026-10-03 | Not Started | Medium | Dave Chen | d.chen@contoso.com | 0 | Contact, demo-request, and newsletter sign-up forms. CRM integration (HubSpot). | GDPR consent must be captured and logged. Test with staging HubSpot sandbox.
Performance Optimisation | Development | 2026-10-01 | 2026-10-10 | Not Started | High | Marcus Webb | m.webb@contoso.com | 0 | Image optimisation, lazy loading, code splitting, CDN config. Target LCP < 2.5s. | Run Lighthouse and WebPageTest before and after. Document delta.
Analytics & Tag Manager Setup | Development | 2026-10-06 | 2026-10-14 | Not Started | Medium | Priya Nair | p.nair@contoso.com | 0 | Configure GA4, GTM, conversion tracking, heatmaps (Hotjar), and data layer. | QA events in Tag Assistant before go-live. Coordinate with marketing on UTM taxonomy.
Development Complete | Development | 2026-10-15 | 2026-10-15 | Not Started | Critical | Marcus Webb | m.webb@contoso.com | 0 | All features built, code reviewed, and merged to staging branch. | Required before QA testing begins. | Yes
Functional & Cross-Browser Testing | QA & Testing | 2026-10-16 | 2026-10-27 | Not Started | Critical | Dave Chen | d.chen@contoso.com | 0 | Test all features across Chrome, Firefox, Edge, Safari (desktop and mobile). | Use BrowserStack. Log all bugs in Jira with severity. Target zero P1 bugs before launch.
Accessibility Audit (Dev) | QA & Testing | 2026-10-22 | 2026-10-29 | Not Started | High | Dave Chen | d.chen@contoso.com | 0 | WCAG 2.1 AA audit on built site: automated (axe) + manual screen reader testing. | Test with NVDA on Windows and VoiceOver on macOS. Document all violations.
UAT with Stakeholders | QA & Testing | 2026-10-28 | 2026-11-06 | Not Started | High | Sarah Chen | s.chen@contoso.com | 0 | User acceptance testing sessions with internal stakeholders and 5 beta customers. | Feedback tracked in shared spreadsheet. Sign-off required from CMO.
SEO & Redirect Mapping | QA & Testing | 2026-10-28 | 2026-11-06 | Not Started | High | Priya Nair | p.nair@contoso.com | 0 | Map all 47 existing URLs to new URLs. Configure 301 redirects. Submit new sitemap. | Screaming Frog crawl before and after launch. Zero 404s on any previously-indexed URL.
QA Sign-Off | QA & Testing | 2026-11-07 | 2026-11-07 | Not Started | Critical | Sarah Chen | s.chen@contoso.com | 0 | All P1/P2 bugs resolved. Stakeholder sign-off received. Launch checklist complete. | No P1 bugs permitted. P2 bugs require documented mitigation plan. | Yes
Content Migration & Final Review | Launch & Post-Launch | 2026-11-03 | 2026-11-13 | Not Started | High | Priya Nair | p.nair@contoso.com | 0 | Migrate and proofread all live content into the new CMS. Final copy approval. | Legal must review Terms, Privacy Policy, and Cookie Policy before publish.
Launch Readiness Review | Launch & Post-Launch | 2026-11-14 | 2026-11-17 | Not Started | Critical | Sarah Chen | s.chen@contoso.com | 0 | Final go/no-go review: all checklist items complete, team on standby, rollback plan confirmed. | Schedule: 10 AM Monday. All leads must attend. Rollback = point DNS back to old site.
Website Go-Live | Launch & Post-Launch | 2026-11-18 | 2026-11-18 | Not Started | Critical | Marcus Webb | m.webb@contoso.com | 0 | DNS cutover, SSL certificate validation, CDN cache purge, smoke test on live URL. | Scheduled for 6 AM to minimise traffic impact. On-call: Marcus (tech), Sarah (comms). | Yes
Launch Announcement Campaign | Launch & Post-Launch | 2026-11-18 | 2026-11-21 | Not Started | High | Priya Nair | p.nair@contoso.com | 0 | Email blast to customer list, social media posts, press release, and blog announcement. | Email draft pre-approved. Schedule social posts in Buffer. Blog post embargoed until go-live.
Post-Launch Monitoring (72h) | Launch & Post-Launch | 2026-11-18 | 2026-11-21 | Not Started | Critical | Marcus Webb | m.webb@contoso.com | 0 | Monitor uptime, error rates, Core Web Vitals, and conversion tracking for 72 hours post-launch. | Alerts configured in Datadog. Escalation path: Marcus → Dave → Sarah.
Post-Launch Review & Retrospective | Launch & Post-Launch | 2026-11-25 | 2026-11-28 | Not Started | Medium | Sarah Chen | s.chen@contoso.com | 0 | Review launch metrics vs KPIs, document lessons learned, and plan Phase 2 backlog. | Target: 20% improvement in bounce rate and 15% uplift in form conversions within 30 days. | Yes