## Tasks
Task Name | Phase | Start Date | Due Date | Status | Priority | Assigned To | Email | % Complete | Description | Dependencies | Notes | Milestone
Project Kickoff | Discovery & Planning | 2026-04-06 | 2026-04-06 | Completed | High | Alex Kumar | a.kumar@contoso.com | 100 | Align executive sponsors, project team, and key stakeholders on scope, budget, and success criteria. |  | Budget of $420k approved. Executive sponsor: CFO. Steering committee meets bi-weekly. | Yes
Requirements Workshops | Discovery & Planning | 2026-04-07 | 2026-04-17 | Completed | Critical | Sarah Chen | s.chen@contoso.com | 100 | Structured workshops with Finance and HR leads to document current-state processes and must-have requirements. | Project Kickoff | 8 workshops completed. 142 requirements captured in Confluence. 23 identified as out-of-scope.
Current System Audit | Discovery & Planning | 2026-04-07 | 2026-04-20 | Completed | High | Marcus Webb | m.webb@contoso.com | 100 | Document all current integrations, data volumes, custom logic, and technical debt in the legacy system. | Project Kickoff | Legacy system has 14 active integrations. 6 require custom connectors. Data spans 8 years (3.2M records).
Technical Architecture Design | Discovery & Planning | 2026-04-21 | 2026-05-01 | Completed | Critical | Marcus Webb | m.webb@contoso.com | 100 | Define target-state architecture: tenant topology, integration patterns, security model, and environment strategy. | Requirements Workshops, Current System Audit | Three environments: Dev, UAT, Prod. Integration hub: Azure API Management. SSO via Azure AD.
Implementation Plan Approved | Discovery & Planning | 2026-05-04 | 2026-05-04 | Completed | Critical | Alex Kumar | a.kumar@contoso.com | 100 | Steering committee sign-off on the full implementation plan: scope, timeline, resource plan, and risk register. | Technical Architecture Design | Approved with one change: go-live window moved from Aug to Sep to avoid fiscal year close. | Yes
Tenant Provisioning & System Setup | Design & Configuration | 2026-05-05 | 2026-05-08 | Completed | Critical | Marcus Webb | m.webb@contoso.com | 100 | Provision ERP tenant; configure environments (Dev, UAT, Prod); set up CI/CD pipeline and admin accounts. | Implementation Plan Approved | All three environments live. Admin credentials in LastPass vault. Azure AD SSO connected.
Master Data Design | Design & Configuration | 2026-05-05 | 2026-05-15 | Completed | High | Sarah Chen | s.chen@contoso.com | 100 | Define master data structures: chart of accounts, cost centers, departments, employee classifications, pay grades. | Implementation Plan Approved | Chart of accounts approved by CFO May 13. 312 cost centers mapped to new structure.
Workflow & Process Configuration | Design & Configuration | 2026-05-11 | 2026-05-29 | In Progress | High | Sarah Chen | s.chen@contoso.com | 70 | Configure approval workflows for AP, AR, expenses, leave requests, and payroll processing. | Implementation Plan Approved | AP and AR workflows complete. Expense and leave in review. Payroll workflow pending HR sign-off.
User Role & Permission Matrix | Design & Configuration | 2026-05-18 | 2026-05-29 | In Progress | High | Priya Nair | p.nair@contoso.com | 50 | Define and configure all user roles, permission sets, and data access rules across Finance and HR modules. | Master Data Design | Finance roles complete (14 roles). HR roles 50% done. Segregation of duties review scheduled May 27.
Integration Architecture & API Specs | Design & Configuration | 2026-04-21 | 2026-05-15 | Completed | High | Marcus Webb | m.webb@contoso.com | 100 | Design API contracts and data-flow diagrams for all 14 integration points. Define error handling and retry logic. | Technical Architecture Design | API specs reviewed and approved. Swagger docs published in internal developer portal.
Design Sign-Off | Design & Configuration | 2026-06-01 | 2026-06-01 | Not Started | Critical | Alex Kumar | a.kumar@contoso.com | 0 | Steering committee review and approval of all configuration decisions before the Build phase begins. | Workflow & Process Configuration, User Role & Permission Matrix, Integration Architecture & API Specs | No build work to proceed until this milestone is cleared. Agenda: demo of configured workflows. | Yes
Data Extraction & Profiling | Data Migration | 2026-05-05 | 2026-05-19 | Completed | High | Dave Chen | d.chen@contoso.com | 100 | Extract full dataset from legacy system; profile data quality issues (nulls, duplicates, format mismatches). | Implementation Plan Approved | 3.2M records extracted. 18% have data quality issues. Top issues: duplicate vendor IDs, missing cost centers, date format inconsistencies.
Data Cleansing | Data Migration | 2026-05-20 | 2026-06-12 | In Progress | Critical | Dave Chen | d.chen@contoso.com | 45 | Remediate all data quality issues identified in profiling. Dedup vendors, backfill cost centers, normalize dates. | Data Extraction & Profiling | Vendor dedup complete (2,847 → 2,103). Cost center backfill 60% done. Date normalization script running.
Migration Mapping Design | Data Migration | 2026-05-20 | 2026-05-29 | Completed | High | Sarah Chen | s.chen@contoso.com | 100 | Map every legacy field to the target ERP schema. Document transformation rules and default values for gaps. | Master Data Design, Data Extraction & Profiling | Full mapping document signed off May 28. 34 transformation rules defined. 6 fields have no legacy equivalent and will use defaults.
Trial Data Migration — Run 1 | Data Migration | 2026-06-15 | 2026-06-26 | Not Started | Critical | Dave Chen | d.chen@contoso.com | 0 | Execute first full trial migration into the DEV environment using the finalized mapping. Measure success rate. | Data Cleansing, Migration Mapping Design, Tenant Provisioning & System Setup | Target: 95%+ clean load. Run validation scripts post-load. Document all rejected records.
Trial Migration Validation | Data Migration | 2026-06-29 | 2026-07-03 | Not Started | Critical | Sarah Chen | s.chen@contoso.com | 0 | Business team verifies migrated data in DEV: vendor balances, employee records, chart of accounts, open POs. | Trial Data Migration — Run 1 | At least 3 Finance and 2 HR super-users must sign off. Issues logged as migration defects in Jira. | Yes
Core Module Build | Build & Integration | 2026-06-02 | 2026-06-26 | Not Started | Critical | Marcus Webb | m.webb@contoso.com | 0 | Build all Finance and HR module configurations in DEV: GL, AP, AR, payroll, leave, and expense management. | Design Sign-Off | Builds follow configuration workbooks. Each module requires peer review before marking complete.
Custom Report Development | Build & Integration | 2026-06-22 | 2026-07-10 | Not Started | High | Dave Chen | d.chen@contoso.com | 0 | Build 12 custom financial and HR reports identified in requirements: P&L, headcount, leave liability, payroll variance. | Core Module Build | Report specs in Confluence. Finance requires 5 reports before UAT; HR requires 4.
Third-Party API Integrations | Build & Integration | 2026-06-22 | 2026-07-10 | Not Started | Critical | Marcus Webb | m.webb@contoso.com | 0 | Build and test all 14 integration connectors: bank feeds, payroll bureau, expense platform, and HRIS data sync. | Integration Architecture & API Specs, Core Module Build | Highest-risk integrations: bank feed (6 banks) and payroll bureau (weekly file exchange). Start these first.
Integration Testing | Build & Integration | 2026-07-13 | 2026-07-24 | Not Started | Critical | Dave Chen | d.chen@contoso.com | 0 | End-to-end integration testing across all 14 connectors using simulated production data volumes. | Custom Report Development, Third-Party API Integrations | Run both happy-path and error-path scenarios. All P1 defects must be resolved before Performance Tuning.
Performance & Load Testing | Build & Integration | 2026-07-27 | 2026-08-07 | Not Started | High | Marcus Webb | m.webb@contoso.com | 0 | Simulate peak load (500 concurrent users, month-end batch). Validate response times and identify bottlenecks. | Integration Testing | Target: < 3s page load at peak. Month-end payroll batch must complete within 2 hours. Use k6 for load scripts.
Build Complete | Build & Integration | 2026-08-10 | 2026-08-10 | Not Started | Critical | Alex Kumar | a.kumar@contoso.com | 0 | Confirm all modules, reports, and integrations are built, tested, and promoted to UAT environment. | Performance & Load Testing, Trial Migration Validation | Gate for Testing phase. Zero P1 bugs permitted in UAT environment. | Yes
System Integration Testing (SIT) | Testing & Training | 2026-08-11 | 2026-08-21 | Not Started | Critical | Dave Chen | d.chen@contoso.com | 0 | Structured SIT across all modules and integrations in UAT environment using scripted test cases. | Build Complete | 180 test cases across Finance (110) and HR (70). Exit criteria: 100% executed, zero P1 open, < 3 P2 open.
User Acceptance Testing (UAT) | Testing & Training | 2026-08-24 | 2026-09-04 | Not Started | Critical | Sarah Chen | s.chen@contoso.com | 0 | Business super-users execute end-to-end business scenarios in UAT. Covers all must-have requirements. | System Integration Testing (SIT) | 15 super-users across Finance and HR. Each scenario must be signed off by the process owner.
End-User Training Delivery | Testing & Training | 2026-08-17 | 2026-09-04 | Not Started | High | Priya Nair | p.nair@contoso.com | 0 | Deliver role-based training to 280 end users across Finance, HR, and department managers. | System Integration Testing (SIT) | Modular e-learning + 4 live instructor sessions. Target: 90%+ completion before go-live. Track via LMS.
Training Sign-Off | Testing & Training | 2026-09-07 | 2026-09-07 | Not Started | High | Priya Nair | p.nair@contoso.com | 0 | Confirm training completion rate ≥ 90% and super-user readiness sign-off from Finance and HR leads. | End-User Training Delivery | Completion data from LMS. Finance lead: CFO. HR lead: CHRO. Both must sign the readiness form. | Yes
UAT Sign-Off | Testing & Training | 2026-09-07 | 2026-09-07 | Not Started | Critical | Alex Kumar | a.kumar@contoso.com | 0 | Steering committee confirmation that UAT exit criteria are met and the system is fit for production. | User Acceptance Testing (UAT) | Gate for go-live authorization. CFO, CHRO, and CTO must countersign. No P1 or P2 bugs outstanding. | Yes
Final Data Migration | Go-Live & Hypercare | 2026-09-08 | 2026-09-11 | Not Started | Critical | Dave Chen | d.chen@contoso.com | 0 | Production data migration using the validated migration scripts. Freeze legacy system at close of business Sep 7. | UAT Sign-Off, Training Sign-Off, Trial Migration Validation | Legacy system read-only from 6 PM Sep 7. Migration window: Sep 8–11. Rollback trigger: < 98% load success rate.
Go-Live Cutover | Go-Live & Hypercare | 2026-09-14 | 2026-09-14 | Not Started | Critical | Alex Kumar | a.kumar@contoso.com | 0 | Execute go-live cutover plan: enable production logins, decommission legacy access, communicate to all users. | Final Data Migration | Go/no-go call at 7 AM Sep 14. All leads on standby. Rollback decision must be made by 10 AM. | Yes
Hypercare Support (4 weeks) | Go-Live & Hypercare | 2026-09-14 | 2026-10-09 | Not Started | High | Marcus Webb | m.webb@contoso.com | 0 | Dedicated on-site and on-call support for the first 4 weeks post go-live. Daily stand-up triage of open issues. | Go-Live Cutover | Full team on standby Week 1. Week 2–4: skeleton crew + on-call. SLA: P1 issues resolved within 4 hours.
Project Close-Out | Go-Live & Hypercare | 2026-10-12 | 2026-10-14 | Not Started | Medium | Alex Kumar | a.kumar@contoso.com | 0 | Formal project closure: lessons learned retrospective, final budget reconciliation, handover to operations team. | Hypercare Support (4 weeks) | Deliverables: lessons learned doc, final status report to steering committee, operations runbook signed off. | Yes